## Sheet1
OUTPUT | ESSENTIAL (£8k+) | REFRESH (£20k+) | TRANSFORMATION (£60k+) | ESSENTIAL (£8k+) | REFRESH (£20k+) | TRANSFORMATION (£60k+) |  | Cost Per Unit | Time Per Unit (Hours) | Units | Total Cost | Total Time (Hours)
TIMELINE | 4-6 weeks | 8-10 weeks | 14-18 weeks | 9340 | 28210 | 66335
PHASE 1: DISCOVERY
Discovery questionnaire | ✅ | ✅ | ✅ | 250 | 250 | 250 |  | 250 | 1 | 1 | 250 | 1
Kickoff meeting/session | ✅ (1 hour) | ✅ (2 hours) | ✅ (2 hours) | 400 | 800 | 800 |  | 400 | 2 | 2 | 800 | 4
Meeting notes + recording | ✅ | ✅ | ✅ | 20 | 40 | 40 |  |  |  |  | 0 | 0
AI transcription summary | ✅ | ✅ | ✅ | 20 | 40 | 40 |  |  |  |  | 0 | 0
Stakeholder interviews | ❌ | 2025-02-01 | 2025-08-05 |  | 740 | 2960 |  |  |  |  | 0 | 0
Stakeholder interview summaries (AI-generated) | ❌ | 2025-02-01 | 2025-08-05 |  | 370 | 740 |  |  |  |  | 0 | 0
Cross-stakeholder synthesis document | ❌ | ❌ | ✅ |  |  | 555 |  |  |  |  | 0 | 0
Asset collection folder | ✅ | ✅ | ✅ | 115 | 115 | 115 |  |  |  |  | 0 | 0
Document repository | ✅ | ✅ | ✅ | 115 | 115 | 115 |  |  |  |  | 0 | 0
Brand guidelines analysis (AI) | ✅ | ✅ | ✅ | 150 | 150 | 150 |  |  |  |  | 0 | 0
Competitor identification | ❌ | 2025-04-03 | 2025-08-05 |  | 300 | 600 |  |  |  |  | 0 | 0
Competitor deep-dive analyses | ❌ | 3-4 (surface) | 5-8 (deep) |  | 600 | 1200 |  |  |  |  | 0 | 0
Competitor comparison table/report | ❌ | ✅ (table) | ✅ (15-20 slides) |  | 150 | 300 |  |  |  |  | 0 | 0
Competitive landscape report | ❌ | ❌ | ✅ (15-20 slides) |  | 300 | 600 |  |  |  |  | 0 | 0
Analytics access setup (GA4 + Search Console) | ❌ | ✅ | ✅ |  | 115 | 115 |  |  |  |  | 0 | 0
GA4 analysis | ❌ | ✅ (basic) | ✅ (deep-dive) |  | 345 | 805 |  |  |  |  | 0 | 0
Search Console analysis | ❌ | ✅ (basic) | ✅ (deep-dive) |  | 345 | 805 |  |  |  |  | 0 | 0
Analytics insights document | ❌ | ✅ (5 pages) | ✅ (5-10 pages) |  | 230 | 575 |  |  |  |  | 0 | 0
Customer interviews | ❌ | ❌ | 2025-05-03 |  |  | 925 |  |  |  |  | 0 | 0
Customer interview summaries (AI-generated) | ❌ | ❌ | 2025-05-03 |  |  | 185 |  |  |  |  | 0 | 0
Customer insights synthesis | ❌ | ❌ | ✅ |  |  | 370 |  |  |  |  | 0 | 0
Customer insight report | ❌ | ❌ | ✅ (10-15 pages) |  |  | 1110 |  |  |  |  | 0 | 0
Persona development | ❌ | ✅ (assumptions doc) | 3-4 (detailed) |  | 450 | 750 |  |  |  |  | 0 | 0
Persona documents | ❌ | ✅ (1 doc) | 3-4 (1-2 pages each) |  | 600 | 1200 |  |  |  |  | 0 | 0
Customer journey mapping (current state) | ❌ | ❌ | ✅ |  |  | 600 |  |  |  |  | 0 | 0
Compliance requirements audit | ❌ | ❌ | ✅ |  |  | 115 |  |  |  |  | 0 | 0
Compliance requirements checklist | ❌ | ❌ | ✅ (5-10 pages) | [7 empty] | 0 | 0
Technical audit | ❌ | ✅ (basic notes) | ✅ (full audit) |  | 500 | 1000 |  |  |  |  | 0 | 0
Technical requirements specification | ❌ | ❌ | ✅ (10-15 pages) |  | 500 | 1000 |  |  |  |  | 0 | 0
Integration requirements specification | ❌ | ❌ | ✅ |  |  | 500 |  |  |  |  | 0 | 0
Platform assessment notes | ❌ | ✅ | ✅ | [7 empty] | 0 | 0
Journey mapping (for new site) | ❌ | ❌ | 2025-06-04 |  |  | 1050 |  |  |  |  | 0 | 0
Journey maps (visual) | ❌ | ❌ | 2025-06-04 | [7 empty] | 0 | 0
Journey synthesis document | ❌ | ❌ | ✅ (5-10 pages) | [7 empty] | 0 | 0
Strategy deck development | ❌ | ❌ | ✅ (30-40 slides) | [7 empty] | 0 | 0
Stakeholder presentation | ❌ | ❌ | ✅ (2 hours) |  |  | 555 |  |  |  |  | 0 | 0
Presentation recording | ❌ | ❌ | ✅ |  |  | 50 |  |  |  |  | 0 | 0
Alignment workshop | ❌ | ❌ | ✅ |  |  | 370 |  |  |  |  | 0 | 0
Alignment notes | ❌ | ❌ | ✅ |  |  | 370 |  |  |  |  | 0 | 0
Discovery summary document | ✅ (2-3 pages) | ✅ (5-10 pages) | ✅ (5-10 pages) | 370 | 925 | 925 |  |  |  |  | 0 | 0
Complete discovery package | ❌ | ❌ | ✅ | [7 empty] | 0 | 0
Team briefing deck | ❌ | ❌ | ✅ | [7 empty] | 0 | 0
Internal team handoff workshop | ❌ | ❌ | ✅ | [7 empty] | 0 | 0
Discovery Phase Subtotal Outputs | 3 | 8 | 23 | 1440 | 7980 | 21840 |  |  |  |  | 0 | 0
PHASE 2: UX
Information architecture development | ✅ | ✅ | ✅ | 150 | 600 | 900
Site map | ✅ (up to 12 pages) | ✅ (up to 25 pages) | ✅ (unlimited) | 150 | 450 | 900
Content matrix | ❌ | ❌ | ✅ |  |  | 345
Content audit (if existing site) | ❌ | ❌ | ✅ |  |  | 345
Content audit spreadsheet | ❌ | ❌ | ✅ |  |  | 345
Navigation architecture document | ❌ | ❌ | ✅
User journey mapping | ❌ | 2-3 (simplified) | 4-6 (with emotions)
Journey flow diagrams | ❌ | 2025-03-02 | 2025-06-04
Touchpoint analysis | ❌ | ❌ | ✅
Touchpoint analysis document | ❌ | ❌ | ✅
Conversion optimization strategy | ❌ | ❌ | ✅
Conversion strategy document | ❌ | ❌ | ✅
Wireframe templates | 2025-05-04 | 2025-08-06 | 10-15 | 750 | 1200 | 2250
Wireframe detail level | Basic (PDF/basic Figma) | Detailed (Figma) | Full (Figma + annotations)
Interactive annotations | ❌ | ❌ | ✅
Prototype | ❌ (static wireframes) | ❌ (static wireframes) | ✅ (clickable) |  |  | 1050
User testing preparation | ❌ | ❌ | ✅ |  |  | 300
User testing script | ❌ | ❌ | ✅
User testing sessions | ❌ | ❌ | 2025-08-05 |  |  | 1800
User testing recordings | ❌ | ❌ | 2025-08-05
User testing analysis | ❌ | ❌ | ✅ |  |  | 600
User testing report | ❌ | ❌ | ✅ |  |  | 1050
Iteration based on testing | ❌ | ❌ | ✅ |  |  | 1575
UX strategy deck | ❌ | ❌ | ✅ (15-20 slides)
UX documentation package | ❌ | ✅ (notes) | ✅ (complete)
Client presentations | 1 | 2 | 3 | 150 | 300 | 450
Revision rounds | 1 | 2 | 3 | 900 | 1200 | 2100
Client feedback documentation | ✅ | ✅ | ✅
UX Phase Subtotal Outputs | 3 | 5 | 15 | 2100 | 3750 | 14010
PHASE 3: DESIGN
Design routes developed | 1 | 2 | 2025-03-02 | 1200 | 2400 | 3600
Design route presentation | ❌ | ✅ | ✅ |  | 225 | 225
Design route presentation deck | ❌ | ✅ | ✅ |  | 450 | 450
Homepage designs | 1 | 2 (routes) + 1 (final) | 2-3 (routes) + 1 (final)
Template designs | 2025-03-02 | 2025-08-06 | 10-15 | 1800 | 4800 | 9000 | ******
Responsive breakpoints | Desktop + mobile | Desktop + mobile | Desktop + tablet + mobile | 900 | 2400 | 4500
Interactive states designed | ❌ | ❌ | ✅ |  |  | 600
Design system development | ❌ | ❌ (basic consistency) | ✅ (full system)
Component library | ✅ (basic Mosaic™) | ✅ (basic Mosaic™) | ✅ (full Mosaic™)
Number of components | Standard only | 15-25 | 30-50 | 1150 | 2875 | 5750
Typography scale documentation | ❌ | ❌ | ✅ |  |  | 150
Color system documentation | ❌ | ❌ | ✅ |  |  | 150
Spacing/grid system documentation | ❌ | ❌ | ✅ |  |  | 150
Design system documentation | ❌ | ❌ | ✅ (complete guide) |  |  | 150
Content strategy development | ❌ | ✅ (basic guidance) | ✅ (full strategy) |  | 150 | 150 | ******
Messaging framework | ❌ | ❌ | ✅ |  |  |  | ******
Tone of voice guidelines | ❌ | ✅ (suggestions) | ✅ (full guidelines) |  | 500 | 1000
SEO content recommendations | ❌ | ✅ (basic) | ✅ (detailed) |  | 460 | 920
Content templates | ❌ | ✅ | ✅ (per page type) |  |  |  | ******
Content guidance document | ❌ | ✅ (2-3 pages) | ✅ (full strategy doc) |  |  |  | ******
Style guide | ❌ | ✅ (basic notes) | ✅ (complete guide)
Developer handoff documentation | ❌ | ❌ | ✅
Design files (Figma) | ✅ | ✅ | ✅ (organized + specs)
Client presentations | 1 | 2 | 3 | 150 | 300 | 450
Revision rounds | 1 | 2 | 3 | 600 | 1920 | 3240
Client feedback documentation | ✅ | ✅ | ✅
Design Phase Subtotal Outputs | 2 | 6 | 12 | 5800 | 16480 | 30485
PHASE 4: DEVELOPMENT
Development environment setup | ✅ | ✅ | ✅
Staging site URL | ✅ | ✅ | ✅
Git repository | ✅ | ✅ | ✅
Mosaic™ Framework installation | ✅ | ✅ | ✅
Template implementation | 4-5 (standard) | 6-8 (custom) | 10-15 (fully custom)
Mosaic™ blocks/components | Standard only | Standard + customized | Advanced custom
Number of custom blocks | 0 | 2025-10-05 | 15-30
Custom functionality | ❌ | ❌ (standard only) | ✅
Number of custom features | 0 | 0 | 2025-08-03
Advanced custom fields | ❌ | ❌ | ✅
Content implementation | Client provides ALL | Client provides (you optimize) | Migration OR client provides
Number of pages content implemented | Up to 12 | Up to 25 | Unlimited
Image optimization | ✅ (basic) | ✅ (standard) | ✅ (full)
Number of images optimized | Up to 50 | Up to 150 | Up to 500
Compliance implementation | ✅ (basic) | ✅ (standard) | ✅ (full FCA/GDPR)
Cookie consent | ✅ | ✅ | ✅
Privacy policy integration | ✅ (link) | ✅ (link + basic) | ✅ (full integration)
Regulatory disclaimers | ❌ | ✅ (basic) | ✅ (comprehensive)
Standard integrations | 2 (GA4 + form) | 2025-04-03 | 2025-06-05
GA4 integration | ✅ | ✅ | ✅
Contact form setup | ✅ (1 form) | ✅ (2-3 forms) | ✅ (multiple forms)
Standard plugins integration | ✅ | ✅ | ✅
Custom integrations | ❌ (add-on only) | ❌ (add-on only) | ❌ (add-on - complex)
Responsive development | Desktop + mobile | Desktop + mobile | Desktop + tablet + mobile
Internal QA rounds | 1 | 2 | 3
Client review rounds (staging) | 1 | 2 | 3
Revision rounds | 1 | 2 | 3
Development documentation | ❌ | ✅ (basic notes) | ✅ (comprehensive)
Development Phase Subtotal Outputs | 4 | 5 | 8
PHASE 5: TESTING
QA testing | ✅ | ✅ | ✅
Browsers tested | 2 (Chrome, Safari) | 3 (Chrome, Safari, Edge) | 5+
Devices tested | Mobile + desktop | Mobile + desktop | Mobile + tablet + desktop
QA report/checklist | ✅ | ✅ | ✅ (comprehensive)
Functional testing | ✅ (forms + links) | ✅ (forms + links + interactions) | ✅ (all functionality)
Accessibility testing | ✅ (automated only) | ✅ (automated only) | ✅ (WCAG 2.1 AA full audit)
Accessibility tools used | Lighthouse | WAVE, Lighthouse, axe | WAVE, Lighthouse, axe + manual
Accessibility report | ✅ (basic check) | ✅ (checklist + remediation) | ✅ (full audit report)
Screen reader testing | ❌ | ❌ | ✅
Keyboard navigation testing | ❌ | ❌ | ✅
Disabled user testing | ❌ (add-on) | ❌ (add-on) | ❌ (add-on)
Performance optimization | ✅ (standard Mosaic™) | ✅ (standard + Core Web Vitals) | ✅ (full optimization <3s target)
Performance report | ✅ (basic check) | ✅ (metrics) | ✅ (before/after report)
Core Web Vitals optimization | ❌ | ✅ | ✅
Security implementation | ✅ (WordPress standards) | ✅ (standard hardening) | ✅ (full hardening + SSL config)
Security report | ❌ | ❌ | ✅
Penetration testing | ❌ (add-on) | ❌ (add-on) | ❌ (add-on)
Bug fixes | ✅ | ✅ | ✅
Testing Phase Subtotal Outputs | 3 | 5 | 8
PHASE 6: LAUNCH PREP
Technical SEO implementation | ✅ (basic) | ✅ (standard) | ✅ (full)
Meta tags | ✅ (basic) | ✅ (all pages) | ✅ (optimized all pages)
XML sitemap | ✅ | ✅ | ✅
Robots.txt | ❌ | ✅ | ✅
Schema markup | ❌ | ❌ | ✅
301 redirects (if migration) | ❌ | ✅ | ✅
Number of redirects | 0 | Up to 50 | Up to 500
SEO documentation | ❌ | ✅ (checklist) | ✅ (audit + implementation doc)
Analytics setup | ✅ (GA4 code) | ✅ (GA4 + basic tracking) | ✅ (GA4 + goals + conversions + events)
GA4 configuration | ✅ (basic) | ✅ (standard) | ✅ (advanced)
Goal/conversion tracking | ❌ | ✅ (basic) | ✅ (comprehensive)
Event tracking | ❌ | ❌ | ✅
Analytics documentation | ❌ | ✅ (setup notes) | ✅ (full documentation)
Mosaic Lens integration | ✅ | ✅ | ✅
Mosaic Lens configuration | ✅ (basic) | ✅ (standard) | ✅ (advanced + custom dashboards)
Training sessions | 1 (30-min walkthrough) | 1 (1-hour session) | 1 (2-hour session)
Training format | Video call | Video call + screen share | Video call + hands-on
Training materials | ✅ (quick start PDF) | ✅ (quick reference guide) | ✅ (documentation + video tutorials)
Mosaic Lens training | ✅ (overview) | ✅ (overview) | ✅ (full training)
CMS training | ✅ (basic) | ✅ (standard) | ✅ (comprehensive)
Launch plan | ❌ | ❌ | ✅
Rollback plan | ❌ | ❌ | ✅
Launch runbook | ❌ | ❌ | ✅
Launch Prep Phase Subtotal Outputs | 3 | 6 | 12
PHASE 7: LAUNCH
Launch type | Standard | Standard | Monitored
Launch execution | ✅ | ✅ | ✅
Post-launch monitoring | ❌ | 24 hours | 48 hours
Launch report | ✅ (URL) | ✅ (checklist) | ✅ (full report)
Launch Phase Subtotal Outputs | 1 | 1 | 1
PHASE 8: POST-LAUNCH
Bug fix warranty | ✅ (7 days) | ❌ (covered by maintenance) | ❌ (covered by maintenance)
Performance review | ❌ | ❌ (add-on) | ✅ (30-day via Mosaic Lens)
Performance report | ❌ | ❌ | ✅ (report + recommendations)
Optimization recommendations | ❌ | ❌ | ✅
Mosaic Lens monitoring | ✅ (with maintenance) | ✅ (with maintenance) | ✅ (with maintenance)
Mosaic™ CMS access | ✅ (ongoing) | ✅ (ongoing) | ✅ (ongoing)
Post-Launch Phase Subtotal Outputs | 1 | 1 | 3
TOTAL PROJECT OUTPUTS | 20 | 37 | 82
ONGOING: HOSTING (SEPARATE)
Recommended hosting package | Bronze (£120/mo) | Silver (£180/mo) | Gold (£240/mo)
Staging server (optional) | £30/mo | £30/mo (recommended) | £30/mo (recommended)
ONGOING: MAINTENANCE (SEPARATE)
Recommended maintenance package | Essential (£280/mo) | Advanced (£395/mo) | Premium (£510/mo)
Mosaic Lens included | ✅ | ✅ | ✅
RECOMMENDED TOTAL MONTHLY | £400-430/mo | £575-605/mo | £750-780/mo
RECOMMENDED TOTAL ANNUAL | £4,800-5,160/year | £6,900-7,260/year | £9,000-9,360/year

## Sheet2
OUTPUT | ESSENTIAL (£8k+) | REFRESH (£20k+) | TRANSFORMATION (£60k+)
TIMELINE | 4-6 weeks | 8-10 weeks | 14-18 weeks
PHASE 1: DISCOVERY
Discovery questionnaire | ✅ | ✅ | ✅
Kickoff meeting/session | ✅ (1 hour) | ✅ (2 hours) | ✅ (2 hours)
Meeting notes + recording | ✅ | ✅ | ✅
AI transcription summary | ✅ | ✅ | ✅
Stakeholder interviews | ❌ | 2025-02-01 | 2025-08-05
Stakeholder interview summaries (AI-generated) | ❌ | 2025-02-01 | 2025-08-05
Cross-stakeholder synthesis document | ❌ | ❌ | ✅
Asset collection folder | ✅ | ✅ | ✅
Document repository | ✅ | ✅ | ✅
Brand guidelines analysis (AI) | ✅ | ✅ | ✅
Competitor identification | ❌ | 2025-04-03 | 2025-08-05
Competitor deep-dive analyses | ❌ | 3-4 (surface) | 5-8 (deep)
Competitor comparison table/report | ❌ | ✅ (table) | ✅ (15-20 slides)
Competitive landscape report | ❌ | ❌ | ✅ (15-20 slides)
Analytics access setup (GA4 + Search Console) | ❌ | ✅ | ✅
GA4 analysis | ❌ | ✅ (basic) | ✅ (deep-dive)
Search Console analysis | ❌ | ✅ (basic) | ✅ (deep-dive)
Analytics insights document | ❌ | ✅ (5 pages) | ✅ (5-10 pages)
Customer interviews | ❌ | ❌ | 2025-05-03
Customer interview summaries (AI-generated) | ❌ | ❌ | 2025-05-03
Customer insights synthesis | ❌ | ❌ | ✅
Customer insight report | ❌ | ❌ | ✅ (10-15 pages)
Persona development | ❌ | ✅ (assumptions doc) | 3-4 (detailed)
Persona documents | ❌ | ✅ (1 doc) | 3-4 (1-2 pages each)
Customer journey mapping (current state) | ❌ | ❌ | ✅
Compliance requirements audit | ❌ | ❌ | ✅
Compliance requirements checklist | ❌ | ❌ | ✅ (5-10 pages)
Technical audit | ❌ | ✅ (basic notes) | ✅ (full audit)
Technical requirements specification | ❌ | ❌ | ✅ (10-15 pages)
Integration requirements specification | ❌ | ❌ | ✅
Platform assessment notes | ❌ | ✅ | ✅
Journey mapping (for new site) | ❌ | ❌ | 2025-06-04
Journey maps (visual) | ❌ | ❌ | 2025-06-04
Journey synthesis document | ❌ | ❌ | ✅ (5-10 pages)
Strategy deck development | ❌ | ❌ | ✅ (30-40 slides)
Stakeholder presentation | ❌ | ❌ | ✅ (2 hours)
Presentation recording | ❌ | ❌ | ✅
Alignment workshop | ❌ | ❌ | ✅
Alignment notes | ❌ | ❌ | ✅
Discovery summary document | ✅ (2-3 pages) | ✅ (5-10 pages) | ✅ (5-10 pages)
Complete discovery package | ❌ | ❌ | ✅
Team briefing deck | ❌ | ❌ | ✅
Internal team handoff workshop | ❌ | ❌ | ✅
Discovery Phase Subtotal Outputs | 3 | 8 | 23
PHASE 2: UX
Information architecture development | ✅ | ✅ | ✅
Site map | ✅ (up to 12 pages) | ✅ (up to 25 pages) | ✅ (unlimited)
Content matrix | ❌ | ❌ | ✅
Content audit (if existing site) | ❌ | ❌ | ✅
Content audit spreadsheet | ❌ | ❌ | ✅
Navigation architecture document | ❌ | ❌ | ✅
User journey mapping | ❌ | 2-3 (simplified) | 4-6 (with emotions)
Journey flow diagrams | ❌ | 2025-03-02 | 2025-06-04
Touchpoint analysis | ❌ | ❌ | ✅
Touchpoint analysis document | ❌ | ❌ | ✅
Conversion optimization strategy | ❌ | ❌ | ✅
Conversion strategy document | ❌ | ❌ | ✅
Wireframe templates | 2025-05-04 | 2025-08-06 | 10-15
Wireframe detail level | Basic (PDF/basic Figma) | Detailed (Figma) | Full (Figma + annotations)
Interactive annotations | ❌ | ❌ | ✅
Prototype | ❌ (static wireframes) | ❌ (static wireframes) | ✅ (clickable)
User testing preparation | ❌ | ❌ | ✅
User testing script | ❌ | ❌ | ✅
User testing sessions | ❌ | ❌ | 2025-08-05
User testing recordings | ❌ | ❌ | 2025-08-05
User testing analysis | ❌ | ❌ | ✅
User testing report | ❌ | ❌ | ✅
Iteration based on testing | ❌ | ❌ | ✅
UX strategy deck | ❌ | ❌ | ✅ (15-20 slides)
UX documentation package | ❌ | ✅ (notes) | ✅ (complete)
Client presentations | 1 | 2 | 3
Revision rounds | 1 | 2 | 3
Client feedback documentation | ✅ | ✅ | ✅
UX Phase Subtotal Outputs | 3 | 5 | 15
PHASE 3: DESIGN
Design routes developed | 1 | 2 | 2025-03-02
Design route presentation | ❌ | ✅ | ✅
Design route presentation deck | ❌ | ✅ | ✅
Homepage designs | 1 | 2 (routes) + 1 (final) | 2-3 (routes) + 1 (final)
Template designs | 2025-03-02 | 2025-08-06 | 10-15
Responsive breakpoints | Desktop + mobile | Desktop + mobile | Desktop + tablet + mobile
Interactive states designed | ❌ | ❌ | ✅
Design system development | ❌ | ❌ (basic consistency) | ✅ (full system)
Component library | ✅ (basic Mosaic™) | ✅ (basic Mosaic™) | ✅ (full Mosaic™)
Number of components | Standard only | 15-25 | 30-50
Typography scale documentation | ❌ | ❌ | ✅
Color system documentation | ❌ | ❌ | ✅
Spacing/grid system documentation | ❌ | ❌ | ✅
Design system documentation | ❌ | ❌ | ✅ (complete guide)
Content strategy development | ❌ | ✅ (basic guidance) | ✅ (full strategy)
Messaging framework | ❌ | ❌ | ✅
Tone of voice guidelines | ❌ | ✅ (suggestions) | ✅ (full guidelines)
SEO content recommendations | ❌ | ✅ (basic) | ✅ (detailed)
Content templates | ❌ | ✅ | ✅ (per page type)
Content guidance document | ❌ | ✅ (2-3 pages) | ✅ (full strategy doc)
Style guide | ❌ | ✅ (basic notes) | ✅ (complete guide)
Developer handoff documentation | ❌ | ❌ | ✅
Design files (Figma) | ✅ | ✅ | ✅ (organized + specs)
Client presentations | 1 | 2 | 3
Revision rounds | 1 | 2 | 3
Client feedback documentation | ✅ | ✅ | ✅
Design Phase Subtotal Outputs | 2 | 6 | 12
PHASE 4: DEVELOPMENT
Development environment setup | ✅ | ✅ | ✅
Staging site URL | ✅ | ✅ | ✅
Git repository | ✅ | ✅ | ✅
Mosaic™ Framework installation | ✅ | ✅ | ✅
Template implementation | 4-5 (standard) | 6-8 (custom) | 10-15 (fully custom)
Mosaic™ blocks/components | Standard only | Standard + customized | Advanced custom
Number of custom blocks | 0 | 2025-10-05 | 15-30
Custom functionality | ❌ | ❌ (standard only) | ✅
Number of custom features | 0 | 0 | 2025-08-03
Advanced custom fields | ❌ | ❌ | ✅
Content implementation | Client provides ALL | Client provides (you optimize) | Migration OR client provides
Number of pages content implemented | Up to 12 | Up to 25 | Unlimited
Image optimization | ✅ (basic) | ✅ (standard) | ✅ (full)
Number of images optimized | Up to 50 | Up to 150 | Up to 500
Compliance implementation | ✅ (basic) | ✅ (standard) | ✅ (full FCA/GDPR)
Cookie consent | ✅ | ✅ | ✅
Privacy policy integration | ✅ (link) | ✅ (link + basic) | ✅ (full integration)
Regulatory disclaimers | ❌ | ✅ (basic) | ✅ (comprehensive)
Standard integrations | 2 (GA4 + form) | 2025-04-03 | 2025-06-05
GA4 integration | ✅ | ✅ | ✅
Contact form setup | ✅ (1 form) | ✅ (2-3 forms) | ✅ (multiple forms)
Standard plugins integration | ✅ | ✅ | ✅
Custom integrations | ❌ (add-on only) | ❌ (add-on only) | ❌ (add-on - complex)
Responsive development | Desktop + mobile | Desktop + mobile | Desktop + tablet + mobile
Internal QA rounds | 1 | 2 | 3
Client review rounds (staging) | 1 | 2 | 3
Revision rounds | 1 | 2 | 3
Development documentation | ❌ | ✅ (basic notes) | ✅ (comprehensive)
Development Phase Subtotal Outputs | 4 | 5 | 8
PHASE 5: TESTING
QA testing | ✅ | ✅ | ✅
Browsers tested | 2 (Chrome, Safari) | 3 (Chrome, Safari, Edge) | 5+
Devices tested | Mobile + desktop | Mobile + desktop | Mobile + tablet + desktop
QA report/checklist | ✅ | ✅ | ✅ (comprehensive)
Functional testing | ✅ (forms + links) | ✅ (forms + links + interactions) | ✅ (all functionality)
Accessibility testing | ✅ (automated only) | ✅ (automated only) | ✅ (WCAG 2.1 AA full audit)
Accessibility tools used | Lighthouse | WAVE, Lighthouse, axe | WAVE, Lighthouse, axe + manual
Accessibility report | ✅ (basic check) | ✅ (checklist + remediation) | ✅ (full audit report)
Screen reader testing | ❌ | ❌ | ✅
Keyboard navigation testing | ❌ | ❌ | ✅
Disabled user testing | ❌ (add-on) | ❌ (add-on) | ❌ (add-on)
Performance optimization | ✅ (standard Mosaic™) | ✅ (standard + Core Web Vitals) | ✅ (full optimization <3s target)
Performance report | ✅ (basic check) | ✅ (metrics) | ✅ (before/after report)
Core Web Vitals optimization | ❌ | ✅ | ✅
Security implementation | ✅ (WordPress standards) | ✅ (standard hardening) | ✅ (full hardening + SSL config)
Security report | ❌ | ❌ | ✅
Penetration testing | ❌ (add-on) | ❌ (add-on) | ❌ (add-on)
Bug fixes | ✅ | ✅ | ✅
Testing Phase Subtotal Outputs | 3 | 5 | 8
PHASE 6: LAUNCH PREP
Technical SEO implementation | ✅ (basic) | ✅ (standard) | ✅ (full)
Meta tags | ✅ (basic) | ✅ (all pages) | ✅ (optimized all pages)
XML sitemap | ✅ | ✅ | ✅
Robots.txt | ❌ | ✅ | ✅
Schema markup | ❌ | ❌ | ✅
301 redirects (if migration) | ❌ | ✅ | ✅
Number of redirects | 0 | Up to 50 | Up to 500
SEO documentation | ❌ | ✅ (checklist) | ✅ (audit + implementation doc)
Analytics setup | ✅ (GA4 code) | ✅ (GA4 + basic tracking) | ✅ (GA4 + goals + conversions + events)
GA4 configuration | ✅ (basic) | ✅ (standard) | ✅ (advanced)
Goal/conversion tracking | ❌ | ✅ (basic) | ✅ (comprehensive)
Event tracking | ❌ | ❌ | ✅
Analytics documentation | ❌ | ✅ (setup notes) | ✅ (full documentation)
Mosaic Lens integration | ✅ | ✅ | ✅
Mosaic Lens configuration | ✅ (basic) | ✅ (standard) | ✅ (advanced + custom dashboards)
Training sessions | 1 (30-min walkthrough) | 1 (1-hour session) | 1 (2-hour session)
Training format | Video call | Video call + screen share | Video call + hands-on
Training materials | ✅ (quick start PDF) | ✅ (quick reference guide) | ✅ (documentation + video tutorials)
Mosaic Lens training | ✅ (overview) | ✅ (overview) | ✅ (full training)
CMS training | ✅ (basic) | ✅ (standard) | ✅ (comprehensive)
Launch plan | ❌ | ❌ | ✅
Rollback plan | ❌ | ❌ | ✅
Launch runbook | ❌ | ❌ | ✅
Launch Prep Phase Subtotal Outputs | 3 | 6 | 12
PHASE 7: LAUNCH
Launch type | Standard | Standard | Monitored
Launch execution | ✅ | ✅ | ✅
Post-launch monitoring | ❌ | 24 hours | 48 hours
Launch report | ✅ (URL) | ✅ (checklist) | ✅ (full report)
Launch Phase Subtotal Outputs | 1 | 1 | 1
PHASE 8: POST-LAUNCH
Bug fix warranty | ✅ (7 days) | ❌ (covered by maintenance) | ❌ (covered by maintenance)
Performance review | ❌ | ❌ (add-on) | ✅ (30-day via Mosaic Lens)
Performance report | ❌ | ❌ | ✅ (report + recommendations)
Optimization recommendations | ❌ | ❌ | ✅
Mosaic Lens monitoring | ✅ (with maintenance) | ✅ (with maintenance) | ✅ (with maintenance)
Mosaic™ CMS access | ✅ (ongoing) | ✅ (ongoing) | ✅ (ongoing)
Post-Launch Phase Subtotal Outputs | 1 | 1 | 3
TOTAL PROJECT OUTPUTS | 20 | 37 | 82
ONGOING: HOSTING (SEPARATE)
Recommended hosting package | Bronze (£120/mo) | Silver (£180/mo) | Gold (£240/mo)
Staging server (optional) | £30/mo | £30/mo (recommended) | £30/mo (recommended)
ONGOING: MAINTENANCE (SEPARATE)
Recommended maintenance package | Essential (£280/mo) | Advanced (£395/mo) | Premium (£510/mo)
Mosaic Lens included | ✅ | ✅ | ✅
RECOMMENDED TOTAL MONTHLY | £400-430/mo | £575-605/mo | £750-780/mo
RECOMMENDED TOTAL ANNUAL | £4,800-5,160/year | £6,900-7,260/year | £9,000-9,360/year

## Copy of Sheet1
OUTPUT | ESSENTIAL (£8k+) | REFRESH (£20k+) | TRANSFORMATION (£60k+) | ESSENTIAL (£8k+) | REFRESH (£20k+) | TRANSFORMATION (£60k+) |  | Cost Per Unit | Time Per Unit (Hours) | Units | Total Cost | Total Time (Hours)
TIMELINE | 4-6 weeks | 8-10 weeks | 14-18 weeks | 6980 | 20325 | 50815
PHASE 1: DISCOVERY
Discovery questionnaire | ✅ | ✅ | ✅ | 250 | 250 | 250 |  | 250 | 1 | 1 | 250 | 1
Kickoff meeting/session | ✅ (1 hour) | ✅ (2 hours) | ✅ (2 hours) | 400 | 800 | 800 |  | 400 | 2 | 2 | 800 | 4
Meeting notes + recording | ✅ | ✅ | ✅ | 20 | 40 | 40 |  |  |  |  | 0 | 0
Stakeholder interviews | ❌ | 2025-02-01 | 2025-08-05 |  | 740 | 2960 |  |  |  |  | 0 | 0
Stakeholder interview summaries (AI-generated) | ❌ | 2025-02-01 | 2025-08-05 |  | 370 | 740 |  |  |  |  | 0 | 0
Cross-stakeholder synthesis document | ❌ | ❌ | ✅ |  |  | 555 |  |  |  |  | 0 | 0
Asset collection folder | ✅ | ✅ | ✅ | 50 | 50 | 50 |  |  |  |  | 0 | 0
Document repository | ✅ | ✅ | ✅ | 50 | 50 | 50 |  |  |  |  | 0 | 0
Competitor identification | ❌ | 2025-04-03 | 2025-08-05 |  | 300 | 600 |  |  |  |  | 0 | 0
Competitor deep-dive analyses | ❌ | 3-4 (surface) | 5-8 (deep) |  | 600 | 1200 |  |  |  |  | 0 | 0
Competitor comparison table/report | ❌ | ✅ (table) | ✅ (15-20 slides) |  | 150 | 300 |  |  |  |  | 0 | 0
Competitive landscape report | ❌ | ❌ | ✅ (15-20 slides) |  | 300 | 600 |  |  |  |  | 0 | 0
Analytics access setup (GA4 + Search Console) | ❌ | ✅ | ✅ |  | 50 | 50 |  |  |  |  | 0 | 0
GA4 analysis | ❌ | ✅ (basic) | ✅ (deep-dive) |  | 345 | 805 |  |  |  |  | 0 | 0
Search Console analysis | ❌ | ✅ (basic) | ✅ (deep-dive) |  | 345 | 805 |  |  |  |  | 0 | 0
Analytics insights document | ❌ | ✅ (5 pages) | ✅ (5-10 pages) |  | 230 | 575 |  |  |  |  | 0 | 0
Customer interviews | ❌ | ❌ | 2025-05-03 |  |  | 925 |  |  |  |  | 0 | 0
Customer interview summaries (AI-generated) | ❌ | ❌ | 2025-05-03 |  |  | 185 |  |  |  |  | 0 | 0
Customer insights synthesis | ❌ | ❌ | ✅ |  |  | 370 |  |  |  |  | 0 | 0
Customer insight report | ❌ | ❌ | ✅ (10-15 pages) |  |  | 1110 |  |  |  |  | 0 | 0
Persona development | ❌ | ✅ (assumptions doc) | 3-4 (detailed) |  | 450 | 750 |  |  |  |  | 0 | 0
Persona documents | ❌ | ✅ (1 doc) | 3-4 (1-2 pages each) |  | 600 | 1200 |  |  |  |  | 0 | 0
Customer journey mapping (current state) | ❌ | ❌ | ✅ |  |  | 600 |  |  |  |  | 0 | 0
Compliance requirements audit | ❌ | ❌ | ✅ |  |  | 115 |  |  |  |  | 0 | 0
Technical requirements specification | ❌ | ❌ | ✅ (10-15 pages) |  | 500 | 1000 |  |  |  |  | 0 | 0
Integration requirements specification | ❌ | ❌ | ✅ |  |  | 500 |  |  |  |  | 0 | 0
Strategy deck development | ❌ | ❌ | ✅ | [7 empty] | 0 | 0
Stakeholder alignment presentation | ❌ | ❌ | ✅ (2 hours) |  |  | 555 |  |  |  |  | 0 | 0
Discovery summary document | ✅ (2-3 pages) | ✅ (5-10 pages) | ✅ (5-10 pages) | 370 | 925 | 925 |  |  |  |  | 0 | 0
Internal team handoff workshop | ✅ | ✅ | ✅ | 500 | 500 | 500 |  |  |  |  | 0 | 0
Discovery Phase Subtotal Outputs |  |  |  | 1640 | 7595 | 19115 |  |  |  |  | 0 | 0
PHASE 2: UX
Information architecture development | ✅ | ✅ | ✅ | 150 | 600 | 900
Site map | ✅ (up to 12 pages) | ✅ (up to 25 pages) | ✅ (unlimited) | 150 | 450 | 900
Content matrix | ❌ | ❌ | ✅ |  |  | 345
Content audit | ❌ | ❌ | ✅ |  |  | 345
User journey mapping | ❌ | 2-3 (simplified) | 4-6 (with emotions) |  | 600 | 900
Touchpoint analysis | ❌ | ❌ | ✅
Wireframe templates | 2025-05-04 | 2025-08-06 | 10-15 | 750 | 1200 | 2250
Prototype | ❌ (static wireframes) | ❌ (static wireframes) | ✅ (clickable) |  |  | 1050 | ******
User testing preparation | ❌ | ❌ | ✅ |  |  | 300 | ******
User testing sessions | ❌ | ❌ | 2025-08-05 |  |  | 1800 | ******
User testing analysis | ❌ | ❌ | ✅ |  |  | 600 | ******
User testing report | ❌ | ❌ | ✅ |  |  | 1050 | ******
Iteration based on testing | ❌ | ❌ | ✅ |  |  | 1575 | ******
UX strategy presentation | ❌ | ❌ | ✅ (15-20 slides) | 300 | 600 | 900
Revision rounds | 1 | 2 | 3 | 900 | 1200 | 2100
UX Phase Subtotal Outputs |  |  |  | 2250 | 4650 | 15015
PHASE 3: DESIGN
Design routes developed | 1 | 2 | 2025-03-02 | 1200 | 2400 | 3600
Design route presentation | ❌ | ✅ | ✅ |  | 225 | 225
Interactive states designed | ❌ | ❌ | ✅ |  |  | 1800 | ******
Number of components | Standard only | 15-25 | 30-50 | 1150 | 2875 | 5750
Responsive breakpoints | Desktop + mobile | Desktop + mobile | Desktop + tablet + mobile | 290 | 720 | 1440
Design system documentation | ❌ | ❌ | ✅ (complete guide) |  |  | 600
Tone of voice guidelines | ❌ | ✅ (suggestions) | ✅ (full guidelines) |  | 500 | 1000 | ******
SEO content recommendations | ❌ | ✅ (basic) | ✅ (detailed) |  | 460 | 920 | ******
Client presentations | 1 | 2 | 3 | 150 | 300 | 450
Revision rounds | 1 | 2 | 3 | 300 | 600 | 900
Design Phase Subtotal Outputs | 2 | 6 | 12 | 3090 | 8080 | 16685
PHASE 4: DEVELOPMENT
Development environment setup | ✅ | ✅ | ✅
Git repository | ✅ | ✅ | ✅
Mosaic™ Framework installation | ✅ | ✅ | ✅
Template implementation | 4-5 (standard) | 6-8 (custom) | 10-15 (fully custom)
Mosaic™ blocks/components | Standard only | Standard + customized | Advanced custom
Custom functionality | ❌ | ❌ (standard only) | ✅ |  |  |  | ******
Number of custom features | 0 | 0 | 2025-08-03 |  |  |  | ******
Advanced custom fields | ❌ | ❌ | ✅ |  |  |  | ******
Content implementation | Client provides ALL | Client provides (you optimize) | Migration OR client provides |  |  |  | ******
Number of pages content implemented | Up to 12 | Up to 25 | Unlimited |  |  |  | ******
Image optimization | ✅ (basic) | ✅ (standard) | ✅ (full)
Cookie consent | ✅ | ✅ | ✅ |  |  |  | ******
Privacy policy integration | ✅ (link) | ✅ (link + basic) | ✅ (full integration) |  |  |  | ******
Standard integrations | 2 (GA4 + form) | 2025-04-03 | 2025-06-05 |  |  |  | ******
GA4 integration | ✅ | ✅ | ✅
Contact form setup | ✅ (1 form) | ✅ (2-3 forms) | ✅ (multiple forms)
Standard plugins integration | ✅ | ✅ | ✅
Custom integrations | ❌ (add-on only) | ❌ (add-on only) | ❌ (add-on - complex) |  |  |  | ******
Internal QA rounds | 1 | 2 | 3
Client review rounds (staging) | 1 | 2 | 3
Revision rounds | 1 | 2 | 3
Development documentation | ❌ | ✅ (basic notes) | ✅ (comprehensive)
Development Phase Subtotal Outputs | 4 | 5 | 8
PHASE 5: TESTING
QA testing | ✅ | ✅ | ✅
Browsers tested | 2 (Chrome, Safari) | 3 (Chrome, Safari, Edge) | 5+
Devices tested | Mobile + desktop | Mobile + desktop | Mobile + tablet + desktop
QA report/checklist | ✅ | ✅ | ✅ (comprehensive)
Functional testing | ✅ (forms + links) | ✅ (forms + links + interactions) | ✅ (all functionality)
Accessibility testing | ✅ (automated only) | ✅ (automated only) | ✅ (WCAG 2.1 AA full audit)
Accessibility tools used | Lighthouse | WAVE, Lighthouse, axe | WAVE, Lighthouse, axe + manual
Accessibility report | ✅ (basic check) | ✅ (checklist + remediation) | ✅ (full audit report)
Screen reader testing | ❌ | ❌ | ✅
Keyboard navigation testing | ❌ | ❌ | ✅
Disabled user testing | ❌ (add-on) | ❌ (add-on) | ❌ (add-on)
Performance optimization | ✅ (standard Mosaic™) | ✅ (standard + Core Web Vitals) | ✅ (full optimization <3s target)
Performance report | ✅ (basic check) | ✅ (metrics) | ✅ (before/after report)
Core Web Vitals optimization | ❌ | ✅ | ✅
Security implementation | ✅ (WordPress standards) | ✅ (standard hardening) | ✅ (full hardening + SSL config)
Security report | ❌ | ❌ | ✅
Penetration testing | ❌ (add-on) | ❌ (add-on) | ❌ (add-on)
Bug fixes | ✅ | ✅ | ✅
Testing Phase Subtotal Outputs | 3 | 5 | 8
PHASE 6: LAUNCH PREP
Technical SEO implementation | ✅ (basic) | ✅ (standard) | ✅ (full)
Meta tags | ✅ (basic) | ✅ (all pages) | ✅ (optimized all pages)
XML sitemap | ✅ | ✅ | ✅
Robots.txt | ❌ | ✅ | ✅
Schema markup | ❌ | ❌ | ✅
301 redirects (if migration) | ❌ | ✅ | ✅
Number of redirects | 0 | Up to 50 | Up to 500
SEO documentation | ❌ | ✅ (checklist) | ✅ (audit + implementation doc)
Analytics setup | ✅ (GA4 code) | ✅ (GA4 + basic tracking) | ✅ (GA4 + goals + conversions + events)
GA4 configuration | ✅ (basic) | ✅ (standard) | ✅ (advanced)
Goal/conversion tracking | ❌ | ✅ (basic) | ✅ (comprehensive)
Event tracking | ❌ | ❌ | ✅
Analytics documentation | ❌ | ✅ (setup notes) | ✅ (full documentation)
Mosaic Lens integration | ✅ | ✅ | ✅
Mosaic Lens configuration | ✅ (basic) | ✅ (standard) | ✅ (advanced + custom dashboards)
Training sessions | 1 (30-min walkthrough) | 1 (1-hour session) | 1 (2-hour session)
Training format | Video call | Video call + screen share | Video call + hands-on
Training materials | ✅ (quick start PDF) | ✅ (quick reference guide) | ✅ (documentation + video tutorials)
Mosaic Lens training | ✅ (overview) | ✅ (overview) | ✅ (full training)
CMS training | ✅ (basic) | ✅ (standard) | ✅ (comprehensive)
Launch plan | ❌ | ❌ | ✅
Rollback plan | ❌ | ❌ | ✅
Launch runbook | ❌ | ❌ | ✅
Launch Prep Phase Subtotal Outputs | 3 | 6 | 12
PHASE 7: LAUNCH
Launch type | Standard | Standard | Monitored
Launch execution | ✅ | ✅ | ✅
Post-launch monitoring | ❌ | 24 hours | 48 hours
Launch report | ✅ (URL) | ✅ (checklist) | ✅ (full report)
Launch Phase Subtotal Outputs | 1 | 1 | 1
PHASE 8: POST-LAUNCH
Bug fix warranty | ✅ (7 days) | ❌ (covered by maintenance) | ❌ (covered by maintenance)
Performance review | ❌ | ❌ (add-on) | ✅ (30-day via Mosaic Lens)
Performance report | ❌ | ❌ | ✅ (report + recommendations)
Optimization recommendations | ❌ | ❌ | ✅
Mosaic Lens monitoring | ✅ (with maintenance) | ✅ (with maintenance) | ✅ (with maintenance)
Mosaic™ CMS access | ✅ (ongoing) | ✅ (ongoing) | ✅ (ongoing)
Post-Launch Phase Subtotal Outputs | 1 | 1 | 3
TOTAL PROJECT OUTPUTS | 20 | 37 | 82
ONGOING: HOSTING (SEPARATE)
Recommended hosting package | Bronze (£120/mo) | Silver (£180/mo) | Gold (£240/mo)
Staging server (optional) | £30/mo | £30/mo (recommended) | £30/mo (recommended)
ONGOING: MAINTENANCE (SEPARATE)
Recommended maintenance package | Essential (£280/mo) | Advanced (£395/mo) | Premium (£510/mo)
Mosaic Lens included | ✅ | ✅ | ✅
RECOMMENDED TOTAL MONTHLY | £400-430/mo | £575-605/mo | £750-780/mo
RECOMMENDED TOTAL ANNUAL | £4,800-5,160/year | £6,900-7,260/year | £9,000-9,360/year